## Stories
Story | Title | Note | Priority | Risk | Estimate | Actual | Iteration | Status
1 | GESTION DES COMPTES UTILISATEURS |  | 1 | 1 | 23 | 35.5 | 1 | Done | Iteration | Estimate | Refactor | Total
2 | GESTION DES PAQUETS DE CARTES |  | 1 | 2 | 48.5 | 43 | 2 | Done | 1 | 38 | 0 | 38
3 | CREATION DE CARTES DANS UN PAQUET |  | 1 | 1 | 15 | 17 | 1 | Done | 2 | 88.5 | 18 | 106.5
4 | ETUDIER UN JEU DE CARTES |  | 1 | 2 | 13 | 8 | 2 | Done | 3 | 105 | 15 | 120
5 | METHODE DE TIRAGE | Done in Story 6 ? | 2 |  |  |  |  | Done | 4 | 102 | 30 | 132
6 | MODES DE JEU |  | 2 | 2 | 27 | 21 | 2 | Done
7 | QUESTIONS DE DIFFERENTS TYPES |  | 3 |  |  |  |  | Skip | Iteration | Actual | Refactor | Total
8 | REPONSES DE DIFFERENTS TYPES |  | 2 | 1 | 35 | 16 | 4 | Done | 1 | 52.5 | 0 | 52.5
9 | STATISTIQUES D’ENTRAINEMENT |  | 3 | 3 | 30 | 37 | 4 | Done | 2 | 72 | 16.5 | 88.5
10 | CONNEXION A UN SERVEUR | Use a BaaS or DB in cloud | 2 | 1 | 50 | 43 | 3 | Done | 3 | 81 | 26 | 107
11 | STORE DE JEUX DE CARTES |  | 3 | 3 | 25 | 18.5 | 4 | Done | 4 | 74.5 | 63 | 137.5
12 | SCORE ET CLASSEMENT |  | 3 |  |  |  |  | Skip
13 | VERSION MOBILE | To hard to complete in time | 3 |  |  |  |  | Skip
14 | LECTURE AUDIO |  | 3 | 3 | 12 | 3 | 4 | Done
15 | IMPORT/EXPORT DE JEUX DE CARTES |  | 2 | 2 | 10 | 8.5 | 3 | Done
16 | IMPRESSION DE JEUX DE CARTES |  | 2 | 2 | 15 | 7 | 3 | Done
17 | LATEX ET HTML DANS LES CARTES |  | 1 | 1 | 30 | 22.5 | 3 | Done
18 | SUCCES |  | 3 |  |  |  |  | Skip
19 | NOTIFICATIONS DE REVISION |  | 3 |  |  |  |  | Skip
20 | CARTES A CHOIX DE DIFFICULTE |  | 2 |  |  |  |  | Skip
21 | CARTES MODULABLES |  | 3 |  |  |  |  | Skip
22 | DUEL |  | 3 |  |  |  |  | Skip
Note on B2: Pour accéder au programme l’utilisateur doit entrer son pseudo et son mot de passe. S’il n’a pas encore de compte, il peut en créer un (local à l’ordinateur) en choisissant un pseudo et un mot de passe. Le logiciel vérifie que le pseudo n’est pas déjà utilisé. Chaque utilisateur aura alors accès à ses propres jeux de cartes et statistiques. Il peut également modifier son mot de passe grâce à un menu d’édition de compte.
Note on B3: L’utilisateur peut créer un jeu de cartes, lui donner un nom et une ou plusieurs catégories (par exemple, le nom d’un cours pour lequel le paquet aide à la révision ou le type de questions qu’on trouve dans le paquet). Une fois le paquet de cartes enregistré, il apparaît dans un menu permettant de parcourir les jeux de cartes. Il est possible de filtrer les jeux de cartes pour n’afficher que ceux qui appartiennent à une certaine catégorie. L’utilisateur peut éga- lement supprimer un jeu de cartes ou le sélectionner pour l’éditer.
Note on B4: Lorsque l’utilisateur édite un paquet de cartes, il peut y ajouter autant de cartes qu’il le souhaite. Chaque carte est composée de deux faces : un recto (contenant une question) et un verso (avec la réponse). Il peut également supprimer une carte ou en modifier une existante.
Note on B5: L’utilisateur peut étudier un jeu de cartes en le sélectionnant dans le menu. Le programme lui présente chaque carte du paquet dans un ordre aléatoire, côté question. Quand l’utilisateur le demande, la réponse est affichée. Il indique alors au programme s’il connaissait ou non la réponse grâce à des boutons. Plusieurs boutons sont disponibles pour indiquer son degré de connaissance : Très bonne, bonne, moyenne, mauvaise ou très mauvaise connaissance.
Note on B6: Quand l’utilisateur étudie un paquet de cartes, l’application lui pré- sente les cartes de sorte à ce que celles qui sont le moins bien connues apparaissent plus souvent.
Note on B7: Deux modes de jeu sont proposés. Le premier est le mode «révision» où les questions les moins maî- trisées reviennent plus souvent de sorte à apprendre la matière. Le second est le mode «libre» où l’utilisateur peut s’amuser libre- ment avec les cartes et essayer d’obtenir le meilleur score sur un jeu de carte choisi.
Note on B8: Lorsqu’un utilisateur crée une carte, il doit pouvoir choisir le type de carte (textuelle, audio, vidéo, ...). On doit pouvoir mélanger les types de cartes dans un même paquet.
Note on B9: Les réponses à une question peuvent être de différente nature : — Texte à trous à compléter — Choix multiple — Réponse ouverte — ...
Note on B10: Le programme offre deux niveaux de statistiques à l’utilisateur. D’abord, des statistiques globales comprennent le temps d’entraî- nement total et par jour, le nombre de jeux de cartes utilisés et une liste des jeux de cartes les plus utilisés. Il donne également accès à des statistiques par paquet de cartes. Celles-ci reprennent le nombre de sessions d’études réalisées sur ce jeu et un indice de maîtrise du paquet. Il permet également de voir l’évolution de ces statistiques au fil des jours sous la forme d’un diagramme d’évolution. Pour chaque paquet, il est possible de voir les cartes triées en fonction de leur connaissance par l’utilisateur.
Note on B11: L’utilisateur peut se connecter à un serveur à l’aide d’un login et d’un mot de passe. Ce serveur retient les jeux de cartes de l’utili- sateur.
Note on B12: Lorsque l’utilisateur est connecté au serveur, il peut se rendre sur un store où il peut publier des jeux de cartes et télécharger ceux publiés par d’autres utilisateurs.
Note on B13: Pour chaque jeu, l’utilisateur peut enregistrer son score basé sur sa connaissance des cartes et sur son temps de réponse. S’il le souhaite, son score est ensuite mis en ligne. L’utilisateur peut ensuite consulter un classement en ligne qui re- cense les scores des joueurs pour chaque jeu de cartes.
Note on B14: L’utilisateur peut se connecter sur son compte à l’aide de son télé- phone et effectuer ses révisions dessus.
Note on B15: Comme certains utilisateurs ont une meilleure mémoire auditive que visuelle, l’utilisateur doit pouvoir se faire dicter le contenu tex- tuel d’une carte à l’aide d’une synthèse vocale.
Note on B16: L’utilisateur peut exporter un jeu de cartes sous forme de fichier. Ce fichier doit être ré-importable dans l’application.
Note on B17: Comme certains utilisateurs préfèrent les supports papiers, l’utili- sateur doit pouvoir exporter ses jeux de cartes sous forme d’image ou de PDF imprimable.
Note on B18: L’utilisateur peut écrire des cartes contenant du code LATEX et/ou HTML qui est correctement interprété lors de la visualisation.
Note on B19: Lorsqu’un utilisateur publie un jeu de cartes sur le store, il peut spécifier des succès qui y sont propres. Un succès se caractérise par un titre, une description et une progression. Des exemples de succès propres aux jeux de cartes sont — Top chrono : Répondre aux questions en un temps minimal — Perfectionniste : Répondre correctement à toutes les ques- tions d’un jeu — ... De plus, le store prévoit des succès génériques qui sont transversaux à tous les jeux de cartes comme — Un nouvel espoir : Mettre son premier score en ligne — Question pour un Champion : Répondre correctement à 100 cartes différentes — Petit producteur : Publier 5 jeux de cartes
Note on B20: L’utilisateur peut spécifier un objectif de révisions, par exemple en nombre de révisions par semaine. L’application envoie des notifi- cations en conséquence pour inciter l’utilisateur à réviser.
Note on B21: Après avoir reçu la question, l’utilisateur a le choix de : — Donner une réponse librement — Demander quatre options pour un choix multiple — Demander deux options pour un choix multiple Le score de l’utilisateur augmentera plus ou moins en fonction de la difficulté choisie en cas de réponse correcte.
Note on B22: Une même question peut avoir des paramètres aléatoires. Par exemple une question demandant de calculer la somme de deux nombres pourrait avoir deux nombres aléatoires comme opé- randes. La réponse correcte sera dépendante de ces paramètres. Il doit donc être possible de créer des formules lors de la création de cartes qui seront évaluées lors de l’affichage de la carte.
Note on B23: Plusieurs utilisateurs peuvent s’affronter dans un mode duel dans lequel la même question est présentée aux joueurs. Chacun gagne des points en fonction de sa performance.

## Task_hours
Please enter your tasks hours here each time your work on a story task. There can be multiple entries for the same date and/or the same task. They will be then summed automatically in other sheets. Please refer - the task ID (see Tasks sheet); the Story and the Title are updated automatically - the current Iteration - the Date you worked on - the Pilote and the Co-pilote - the number of Hours worked These real hours are reflected automatically in Calendar and in Tasks. Calendar should not be modified. Tasks should only be modified when adding a new task or modifying an existing one.
ID | Iteration | Story | Title | Date | Pilote | Co-Pilote | Hours
C2-3 | 2 | C2 | EditDeck (FXML): Create deck list table | 2023-03-16 | Antoine | Elliot | 1
C2-14 | 2 | C2 | DeckList (ProfileController): Pass deck ID from profile view to deckEdit view when pushing edit btn | 2023-03-16 | Elliot | Antoine | 1
D3-1 | 2 | D3 | Tracking: task excel on google sheets | 2023-03-16 | Antoine | Luca | 1
D3-2 | 2 | D3 | Tracking: Burndown Chart | 2023-03-16 | Luca | Antoine | 1
D2-3 | 2 | D2 | Refactor: Fix layout for the SignIn & SignUp view | 2023-03-17 | Francesco | Dave | 1
D2-1 | 2 | D2 | Refactor: Split the SignIn & SignUp controller | 2023-03-17 | Francesco | Dave | 1
D2-2 | 2 | D2 | Refactor: Split the Profile & Settings Controller | 2023-03-17 | Elliot | Antoine | 1
D2-2 | 2 | D2 | Refactor: Split the Profile & Settings Controller | 2023-03-17 | Luca | Ismael | 1
D4-1 | 2 | D4 | Docs: refaire le README.md | 2023-03-17 | Francesco | Dave | 0.5
C4-1 | 2 | C4 | Study: Refactor the editDeck view into the static Study view (FlashCard view) | 2023-03-19 | Luca | Emile | 2
C2-2 | 2 | C2 | EditDeck (FXML): Create global title and edit buttons | 2023-03-19 | Antoine | Elliot | 1.5
C2-3 | 2 | C2 | EditDeck (FXML): Create deck list table | 2023-03-19 | Antoine | Elliot | 1.5
C2-4 | 2 | C2 | EditDeck (DeckEditController): Load fake deck cards dynamically in list | 2023-03-19 | Antoine | Elliot | 0.5
C4-1 | 2 | C4 | Study: Refactor the editDeck view into the static Study view (FlashCard view) | 2023-03-27 | Luca | Emile | 1
C2-10 | 2 | C2 | Deck List: Deck creation & deletion from the view | 2023-03-27 | Théo | Luca | 2.5
C2-5 | 2 | C2 | EditDeck(FXML): Edit button popup to edit question and answer | 2023-03-27 | Antoine | Elliot | 2
C2-1 | 2 | C2 | DB: Create Deck & Card model in database (CRUD) | 2023-03-19 | Dave | Anton | 4
D5-1 | 2 | D5 | Refactor: navigation manager design | 2023-03-27 | Luca | Antoine | 1
D5-2 | 2 | D5 | Refactor: navigation manager implementation | 2023-03-27 | Luca | Antoine | 1
C2-1 | 2 | C2 | DB: Create Deck & Card model in database (CRUD) | 2023-03-27 | Dave | Anton | 3
C6-1 | 2 | C6 | Study Mode: Implement the "Review" study mode | 2023-03-19 | Ben David | Francesco | 6
C6-2 | 2 | C6 | Study Mode: Implement the "Free" study mode | 2023-03-27 | Ben David | Francesco | 4
C2-15 | 2 | C2 | EditDeck(FXML): Add card popup | 2023-03-30 | Elliot | Antoine | 0.5
C2-16 | 2 | C2 | EditDeck(FXML): edit title and category popups | 2023-03-30 | Elliot | Antoine | 0.5
C2-6 | 2 | C2 | EditDeck(DeckEditController): Edit button logic to edit question and answer in popup | 2023-03-30 | Elliot | Antoine | 1
C2-7 | 2 | C2 | EditDeck(FXML): Delete button to delete question | 2023-03-30 | Elliot | Antoine | 0.5
C2-8 | 2 | C2 | EditDeck(DeckEditController): Delete button logic to delete question | 2023-03-30 | Elliot | Antoine | 0.5
C2-9 | 2 | C2 | EditDeck(DeckEditController) : Edit deck properties logic (title, category) | 2023-03-30 | Elliot | Antoine | 0.5
C2-18 | 2 | C2 | EditDeck(FXML): make vboxes question/answer for cards | 2023-03-31 | Luca | Antoine | 1
C2-20 | 2 | C2 | EditDeck(FXML): Add scrolling in edit deck view | 2023-03-31 | Antoine | Luca | 0.5
C6-4 | 2 | C6 | Study Mode: Implements the tests | 2023-03-29 | Francesco | Ben David | 1.5
C2-21 | 2 | C2 | DeckList(FXML): Add scrolling in DeckList/Profile/settings view | 2023-04-02 | Ismael | Dave | 1
C2-22 | 2 | C2 | DeckList(FXML): text wrapping for DeckList/Profile view | 2023-04-02 | Dave | Ismael | 1
C2-23 | 2 | C2 | EditDeck(FXML): add category in view | 2023-04-02 | Dave | Ismael | 2
C2-1 | 2 | C2 | DB: Create Deck & Card model in database (CRUD) | 2023-04-02 | Anton | Dave | 3
C2-26 | 2 | C2 | Fix(Database): Tables are created only when calling getInstance() | 2023-04-02 | Luca | Ismael | 0.5
C2-11 | 2 | C2 | Deck List: Load decks from the database in the view | 2023-04-02 | Ismael | Dave | 1
C6-6 | 2 | C6 | Study Mode: create a view for "Free" study mode | 2023-04-17 | Théo | Dave | 1.5
D6-1 | 2 | D6 | Refactor: handling all runtime errors in code; replace signature errors in try/catch blocks | 2023-04-17 | Francesco | Ismael | 3
D5-3 | 2 | D5 | Feat: Add params in navigation | 2023-04-17 | Luca | Antoine | 1.5
C4-2 | 2 | C4 | Study: Load cards from database into Study view | 2023-04-17 | Emile | Théo | 1.5
C2-27 | 2 | C2 | DB: Create interface between controller & database for managing decks & cards | 2023-04-17 | Luca | Francesco | 3
C6-3 | 2 | C6 | Study Mode: Create a controller for "Review" Mode | 2023-04-17 | Francesco | Luca | 4
C4-2 | 2 | C4 | Study: Load cards from database into Study view | 2023-04-17 | Emile | Théo | 2.5
C4-4 | 2 | C4 | Study: Add text wrapping in Study view for answer & question | 2023-04-17 | Francesco | Ismael | 0.5
C4-2 | 2 | C4 | Study: Load cards from database into Study view | 2023-04-17 | Emile | Théo | 0.5
C2-13 | 2 | C2 | DeckList (FXML): Delete button warning popup to delete deck & card | 2023-03-17 | Théo | Dave | 0.5
D1-1 | 2 | D1 | CI/CD: Create a CI/CD action to test, check format & build | 2023-04-17 | Anton | Ben David | 3.5
C2-19 | 2 | C2 | EditDeck(docs): make docstrings and comments for all classes | 2023-04-17 | Francesco |  | 2.5
C6-5 | 2 | C6 | Study Mode: Refactor Sutdy views and handle exceptions | 2023-04-17 | Dave | Théo | 4
C2-12 | 2 | C2 | Deck List: Filter deck by category/theme | 2023-04-17 | Antoine | Ismael | 3.5
C2-28 | 2 | C2 | Refactor(Database): Remove the perfomanceType entity (replace with simple integer) | 2023-04-17 | Théo | Dave | 0.5
C2-29 | 2 | C2 | Fix(Database): Fixed issue in test caused by database, refactor database | 2023-04-17 | Luca |  | 2.5
D7-1 | 3 | D7 | Refactor: fix refresh list when adding new decks with unknown tag | 2023-04-18 | Antoine |  | 1.5
D7-12 | 3 | D7 | MVC: Refactor the view controllers and controllers to respect the MVC patterns | 2023-04-18 | Luca |  | 3
C10-1 | 3 | C10 | Server: Setup Django App with Docker Compose (Initial Setup) + Architecture | 2023-04-19 | Elliot | Anton | 3
D7-12 | 3 | D7 | MVC: Refactor the view controllers and controllers to respect the MVC patterns | 2023-04-19 | Luca |  | 1
C15-2 | 3 | C15 | Export/import: Serialize/Deserialize deck (JSON) and export to file (or create deck) | 2023-04-20 | Elliot | Emile | 1
C15-1 | 3 | C15 | FXML: Add dropdown buttons on the UI to Export/Import JSON on the ProfileView + File Browser + PDF | 2023-04-20 | Elliot | Emile | 0.5
D7-10 | 3 | D7 | Refactor: Manage the navigation in a different way (controller should choose to change view!) | 2023-04-20 | Luca | Ismael | 2
C10-2 | 3 | C10 | Server: ORM Models in Django + Admin Interface | 2023-04-21 | Dave | Anton | 3
C10-3 | 3 | C10 | Server: Serializers and Deserializers (JSON) | 2023-04-22 | Antoine | Luca | 1
C16-1 | 3 | C16 | FXML: Add buttons on the UI to download PDF (Add option in Export ?) | 2023-04-23 | Antoine | Dave | 0.5
C16-2 | 3 | C16 | PDF: Add logic to download PDF | 2023-04-23 | Antoine | Dave | 2
D7-10 | 3 | D7 | Refactor: Manage the navigation in a different way (controller should choose to change view!) | 2023-04-24 | Luca | Ismael | 0.5
C17-2 | 3 | C17 | Client: Parse LaTeX | 2023-04-24 | Ismael | Francesco | 1
C10-8 | 3 | C10 | Finish setting up docker and django | 2023-04-24 | Anton | Francesco | 2.5
C16-3 | 3 | C16 | PDF: Format PDF | 2023-04-24 | Dave | Antoine | 1
C16-5 | 3 | C16 | PDF: Add popup when a deck is downloaded | 2023-04-24 | Dave | Antoine | 0.5
C17-3 | 3 | C17 | Client: Parse HTML | 2023-04-25 | Ben David | Dave | 2
C10-9 | 3 | C10 | Finish api (tests + security) | 2023-04-25 | Anton | Dave | 2
C15-2 | 3 | C15 | Export/import: Serialize/Deserialize deck (JSON) and export to file (or create deck) | 2023-04-25 | Elliot | Emile | 1.5
C17-4 | 3 | C17 | FXML: Create a radio button when inputting card to let the user decide what kind of input he wants | 2023-04-25 | Dave | Ismael | 1.5
D7-11-1 | 3 | D7 | FXML: Empty EditCardView : Question/Answer is empty ¦ CreateDeck : Deckname/Tag is empty--> Add Popup | 2023-04-25 | Ismael |  | 0.5
C10-5 | 3 | C10 | Server: Generate Swagger docs | 2023-04-26 | Ismael | Théo | 2
D7-13 | 3 | D7 | ci: refactor CI/CD + build Django docker image | 2023-04-26 | Luca |  | 2
D7-11 | 3 | D7 | FXML: Popups should be styled the same as the rest of the application | 2023-04-26 | Théo | Ismael | 3
D7-7 | 3 | D7 | Service: Create a UserService with DTOs + Refactor | 2023-04-27 | Luca | Théo | 1
C17-9 | 3 | C17 | FXML + Client: Add HTMLView in editDeck | 2023-04-27 | Ben David | Ismael | 5
C10-4 | 3 | C10 | Server: Deployment (on Cloud) + DNS | 2023-04-27 | Ben David | Luca | 3
C10-7 | 3 | C10 | Client: Refactor services (Call HTTP API) with swapped pilot-copilot | 2023-04-28 | Dave | Francesco | 5
C10-6 | 3 | C10 | Client: Refactor services (Call HTTP API) | 2023-04-28 | Francesco | Dave | 6
C16-4 | 3 | C16 | PDF: format A6 for cards | 2023-04-28 | Ismael | Antoine | 3
C17-5 | 3 | C17 | FXML:: Create a webView when studying HTML | 2023-04-28 | Théo | Ben David | 2.5
C17-7 | 3 | C17 | FXML + Client: Add latexView in editDeck | 2023-04-28 | Francesco | Ben David | 3
C17-6 | 3 | C17 | Django DB: Add question type and answer type to database | 2023-04-28 | Ismael | Anton | 3
C17-11 | 3 | C17 | FXML + Client + Refactor: Refactor HTML, LaTeX, plain text into learning mode | 2023-03-28 | Francesco | Ben David | 1
C17-8 | 3 | C17 | FXML + Client: Add latexView in learningMode | 2023-03-28 | Francesco | Ben David | 1.5
C15-2 | 3 | C15 | Export/import: Serialize/Deserialize deck (JSON) and export to file (or create deck) | 2023-04-29 | Elliot | Emile | 2
C10-4 | 3 | C10 | Server: Deployment (on Cloud) + DNS | 2023-04-29 | Ben David | Luca | 1.5
C10-11 | 3 | C10 | Server: Bug fixes and tags server side | 2023-04-29 | Anton | Francesco | 2
C10-10 | 3 | C10 | Server: Add API for Sign Up (create an account) + edit password | 2023-04-29 | Anton | Ismael | 1
C10-13 | 3 | C10 | Refactor services | 2023-04-30 | Dave |  | 2
C15-2 | 3 | C15 | Export/import: Serialize/Deserialize deck (JSON) and export to file (or create deck) | 2023-04-30 | Elliot | Emile | 1
C10-13 | 3 | C10 | Refactor services | 2023-04-30 | Anton | Ben David | 1
D7-7 | 3 | D7 | Service: Create a UserService with DTOs + Refactor | 2023-04-30 | Luca | Théo | 1
D7-15 | 3 | D7 | Refactor + FXML + Client: Fix Review Mode | 2023-04-30 | Francesco |  | 1.5
C10-15 | 3 | C10 | fix tags in UI + refactor | 2023-05-01 | Anton |  | 2
C10-16 | 3 | C10 | API Client bug fixes | 2023-04-30 | Dave | Anton | 3
D7-7 | 3 | D7 | Service: Create a UserService with DTOs + Refactor | 2023-05-01 | Luca | Théo | 3
C15-3 | 3 | C15 | Export/Import: Rewrite tests | 2023-04-30 | Emile |  | 1
D7-17 | 3 | D7 | Refactor error handling | 2023-05-01 | Anton |  | 2
C15-1 | 3 | C15 | FXML: Add dropdown buttons on the UI to Export/Import JSON on the ProfileView + File Browser + PDF | 2023-05-01 | Elliot | Emile | 1.5
D7-18 | 3 | D7 | Bug: fix the json deck exporter file chooser not working properly | 2023-05-01 | Antoine | Emile | 1
C17-12 | 3 | C17 | Refactor + client + server: Make card use card type and not be statically bound | 2023-05-01 | Francesco | Anton | 2
C10-15 | 3 | C10 | fix tags in UI + refactor | 2023-04-30 | Anton | Ben David | 2
D7-14 | 3 | D7 | CreateCard: add length limit to size of question and answer (e.g. max 250 chars per question or per answer) | 2023-05-01 | Théo | Ismael | 2.5
D7-19 | 3 | D7 | Refactor: Profile view add deck mth | 2023-05-01 | Antoine |  | 1
D8-001 | 4 | D8 | Fix: Fix issue in import/export | 2023-05-06 | Elliot | Luca | 0.5
C11-003 | 4 | C11 | FXML: Add View for store + ViewController | 2023-05-06 | Elliot | Luca | 1.5
C11-001 | 4 | C11 | Database: Review Database model for the store + API | 2023-05-06 | Luca | Elliot | 1
C9-004 | 4 | C9 | FXML: Add menu for GLOBAL stats (between Home and Settings) | 2023-05-07 | Théo | Ismael | 1
C8-003 | 4 | C8 | FXML: Handle different card type in all learning mode | 2023-05-07 | Dave | Emile | 2
C11-003 | 4 | C11 | FXML: Add View for store + ViewController | 2023-05-07 | Elliot | Luca | 2
C9-004 | 4 | C9 | FXML: Add menu for GLOBAL stats (between Home and Settings) | 2023-05-08 | Théo | Ismael | 6
C9-002 | 4 | C9 | Service: Create a Service for the Statistics API | 2023-05-08 | Ben David | Théo | 1.5
C11-003 | 4 | C11 | FXML: Add View for store + ViewController | 2023-05-08 | Elliot |  | 1.5
C9-002 | 4 | C9 | Service: Create a Service for the Statistics API | 2023-05-09 | Ben David | Théo | 3.5
C8-003 | 4 | C8 | FXML: Handle different card type in all learning mode | 2023-05-08 | Dave | Emile | 2
C9-001 | 4 | C9 | Database: Model for statistics + Django API | 2023-05-09 | Anton | Antoine | 1
C11-001 | 4 | C11 | Database: Review Database model for the store + API | 2023-05-09 | Luca | Elliot | 1.5
C8-002 | 4 | C8 | FXML: Question Type and Answer Type should be in the card dialog | 2023-05-10 | Luca | Dave | 2
C8-004 | 4 | C8 | Model: Handle different card type in Cards | 2023-05-10 | Francesco | Dave | 1.5
C11-004 | 4 | C11 | FXML: add carousel for most popular decks | 2023-05-10 | Elliot | Antoine | 3.5
C8-002 | 4 | C8 | FXML: Question Type and Answer Type should be in the card dialog | 2023-05-10 | Luca | Dave | 1.5
C14-002 | 4 | C14 | FXML: Add logic to dictate answer OR question in Controller | 2023-05-10 | Francesco | Dave | 2
C11-004 | 4 | C11 | FXML: add carousel for most popular decks | 2023-05-10 | Antoine | Elliot | 1.5
D8-006 | 4 | D8 | FXML: Add help button in modes and edit card dialog to show how to format questions | 2023-05-10 | Francesco |  | 0.5
C11-005 | 4 | C11 | FXML: show all decks on the store | 2023-05-10 | Elliot | Antoine | 1.5
C11-001 | 4 | C11 | Database: Review Database model for the store + API | 2023-05-10 | Luca | Elliot | 1
D8-006 | 4 | D8 | FXML: Add help button in modes and edit card dialog to show how to format questions | 2023-05-10 | Francesco |  | 1
D8-008 | 4 | D8 | Cache: Cache decks and make it not make it a request everytime | 2023-05-10 | Francesco | Ben David | 2.5
C8-003 | 4 | C8 | FXML: Handle different card type in all learning mode | 2023-05-10 | Dave | Emile | 1
C8-003 | 4 | C8 | FXML: Handle different card type in all learning mode | 2023-05-10 | Dave | Emile | 2.5
C9-001 | 4 | C9 | Database: Model for statistics + Django API | 2023-05-10 | Anton | Antoine | 6
C8-003 | 4 | C8 | FXML: Handle different card type in all learning mode | 2023-05-11 | Dave | Emile | 2
C9-002 | 4 | C9 | Service: Create a Service for the Statistics API | 2023-05-10 | Ben David | Théo | 2
C11-006 | 4 | C11 | StoreDeckService: api call for popular and all decks | 2023-05-11 | Antoine | Luca | 1.5
C11-008 | 4 | C11 | StoreDeckService : share deck api call | 2023-05-11 | Luca | Antoine | 0.5
C11-007 | 4 | C11 | StoreDeckService: download storedeck api call | 2023-05-11 | Antoine | Luca | 0.5
C8-003 | 4 | C8 | FXML: Handle different card type in all learning mode | 2023-05-11 | Dave |  | 1.5
D8-009 | 4 | D8 | Refactor: Use SonarLint to refactor code | 2023-05-11 | Ben David | Francesco | 1
C14-001 | 4 | C14 | FXML: Add button with Speaker Icon in learning modes | 2023-05-11 | Dave | Francesco | 1
C9-004 | 4 | C9 | FXML: Add menu for GLOBAL stats (between Home and Settings) | 2023-05-12 | Ismael | Ben David | 6
C11-009 | 4 | C11 | StoreDeckService: search for deck in catalog | 2023-05-12 | Antoine | Elliot | 1
D8-014 | 4 | D8 | Refactor: Create custom component for Deck in ProfileDeckViewController | 2023-05-12 | Francesco | Luca | 0.5
D8-017 | 4 | D8 | Refactor: Create custom component for Deck in StoreDeckViewController - Populars | 2023-05-12 | Antoine |  | 2.5
D8-015 | 4 | D8 | Refactor: Create custom component for Card in EditDeckViewController | 2023-05-12 | Francesco | Ben David | 2.5
D8-018 |  |  |  | 2023-05-12 | Luca |  | 1
D8-020 | 4 | D8 | Refactor: Fix issues with Docker + add persistent volume for Postgres Database | 2023-05-12 | Luca |  | 0.5
D8-021 | 4 | D8 | Refactor: Add method in AbstractViewController to open FileBrowser | 2023-05-12 | Luca | Anton | 0.5
D8-007 | 4 | D8 | DP: Use the Visitor Design Pattern to handle different modes | 2023-05-11 | Emile | Anton | 3
D8-019 | 4 | D8 | Refactor: Add method for TextInputDialog | 2023-05-13 | Luca |  | 0.5
C9-004 | 4 | C9 | FXML: Add menu for GLOBAL stats (between Home and Settings) | 2023-05-13 | Ismael | Théo | 8
D8-022 | 4 | D8 | Feature: progress indicator for API calls | 2023-05-14 | Anton |  | 5
D8-016 | 4 | D8 | Refactor: Create custom component for Deck in StoreDeckViewController - Spotlight | 2023-05-13 | Ben David | Francesco | 1
D8-025 | 4 | D8 | Refactor: D8-024 with different pilots | 2023-05-15 | Luca | Francesco | 3.5
D8-026 | 4 | D8 | Refactor: Remove card and replace it with abstract card and replace instantiation in services with parsers | 2023-05-15 | Luca | Francesco | 1.5
D8-003 | 4 | D8 | Tests: tests for userService | 2023-05-15 | Luca | Dave | 1.5
D8-026 | 4 | D8 | Refactor: Remove card and replace it with abstract card and replace instantiation in services with parsers | 2023-05-16 | Luca | Francesco | 3
D8-004 | 4 | D8 | Tests: Configure Mockito + tests for tagService | 2023-05-16 | Dave | Luca | 1.5
D8-026 | 4 | D8 | Refactor: Remove card and replace it with abstract card and replace instantiation in services with parsers | 2023-05-18 | Francesco | Luca | 3
D8-011 | 4 | D8 | PDF: Make PDF download choose location to save | 2023-05-20 | Francesco | Ben David | 0.5
D8-027 | 4 | D8 | Code: General code refactor | 2023-05-20 | Francesco |  | 2
D8-030 | 4 | D8 | Tests: tests model for all modes | 2023-05-21 | Dave | Ismael | 2
D8-029 | 4 | D8 | Learning Mode: check all learning views and controllers (add docstrings, remove fixme, remove controls in view) | 2023-05-21 | Dave |  | 2.5
D8-028 | 4 | D8 | FXML + Client: Make user not go to review mode if deck is empty | 2023-05-20 | Francesco |  | 0.5
D8-013 | 4 | D8 | Refactor: Remove calculation logic outside of model | 2023-05-19 | Francesco | Luca | 1.5
D8-032 | 4 | D8 | Javadoc | 2023-05-21 | Antoine |  | 2
D8-037 | 4 | D8 | Test parsers | 2023-05-21 | Elliot |  | 2
D8-010 | 4 | D8 | Thread: Make PDF use a thread to not block the execution of the app | 2023-05-14 | Ben David | Francesco | 1
D8-011 | 4 | D8 | PDF: Make PDF download choose location to save | 2023-05-14 | Francesco | Ben David | 0.5
C9-001 | 4 | C9 | Database: Model for statistics + Django API | 2023-05-16 | Ben David |  | 2
D8-040 | 4 | D8 | handle cloze based text card on edit Deck view | 2023-05-22 | Dave | Ben David | 2
D8-031 | 4 | D8 | Text to speech: remove static methods | 2023-05-22 | Ismael |  | 1
D8-034 | 4 | D8 | Fix old Jar files | 2023-05-22 | Ben David | Dave | 0.5
D8-006 | 4 | D8 | FXML: Add help button in modes and edit card dialog to show how to format questions | 2023-05-22 | Théo | Emile | 2.5
D8-035 | 4 | D8 | Refactor: EditCardDialog | 2023-05-22 | Emile | Théo | 4
D8-033 | 4 | D8 | Demo | 2023-05-22 | Dave |  | 1.5
D8-032 | 4 | D8 | Javadoc | 2023-05-22 | Antoine |  | 2

## Tasks
C stories are Customer Stories D stories are Developer Stories
ID | Iteration | Story | Priority | Task | Pilote | Co-Pilote | Estimate | Real | Deadline | Status | Notes
C1-1 | 1 | C1 | 1 | Mise en place Maven front-end | Luca | Antoine | 0.5 | 1 |  | Done
C1-2 | 1 | C1 | 1 | Mise en place font custom | Antoine | Luca | 0.25 | 1 |  | Done
C1-3 | 1 | C1 | 1 | Mise en place classes principales | Luca | Antoine | 0.25 | 0.5 |  | Done
C1-4 | 1 | C1 | 1 | Création d’un component pour le layout | Luca | Antoine | 0.5 | 1 |  | Done
C1-5 | 1 | C1 | 1 | Création styles de base | Antoine | Luca | 1 | 2 |  | Done
C1-6 | 1 | C1 | 1 | Création vue profil | Antoine | Luca | 1 | 1 |  | Done
C1-7 | 1 | C1 | 1 | Création de la vue settings | Luca | Antoine | 1 | 0.5 |  | Done
C1-8 | 1 | C1 | 1 | Style vue profil | Antoine | Luca | 1 | 2 |  | Done
C1-9 | 1 | C1 | 1 | Style vue settings | Luca | Antoine | 1 | 1 |  | Done
C1-10 | 1 | C1 | 1 | Liaisons avec les vues Login et Signup | Antoine | Luca | 0.5 | 0.5 |  | Done
C1-11 | 1 | C1 | 1 | Génération dynamique d’éléments UI dans profil et settings | Luca | Antoine | 0.5 | 0.5 |  | Done
C1-12 | 1 | C1 | 1 | Documentation Javadoc | Antoine | Luca | 0.5 | 1 |  | Done
C1-13 | 1 | C1 | 1 | Intégration login/signup – profil/settings – deck view | Antoine | Luca | 1 | 1.5 |  | Done
C1-14 | 1 | C1 | 1 | Mise en place Maven back-end | Ben David | Anton | 1.5 | 4 |  | Done
C1-15 | 1 | C1 | 1 | Mise en place ORM lite | Anton | Ben David | 1 | 2.5 |  | Done
C1-16 | 1 | C1 | 1 | Création tables User et tests | Anton | Elliot | 1 | 1 |  | Done
C1-17 | 1 | C1 | 1 | Création UserDatabase et tests | Ben David | Anton | 1 | 1 |  | Done
C1-18 | 1 | C1 | 1 | Implémentation algo hash et tests | Ben David | Anton | 1 | 1.5 |  | Done
C1-19 | 1 | C1 | 1 | Liaison avec les vues login/sign up | Ben David | Anton | 0.5 | 1 |  | Done
C1-20 | 1 | C1 | 1 | Installation et configuration de JavaFX, Maven et Scene-Builder | Dave | Ismael | 1 | 1 |  | Done
C1-21 | 1 | C1 | 1 | Ajout des dépendances Maven pour JavaFX et JFoenix dans le pom.xml | Dave | Ismael | 0.25 | 0.5 |  | Done
C1-22 | 1 | C1 | 1 | Création du fxml pour le SignIn view | Dave | Ismael | 1 | 2 |  | Done
C1-23 | 1 | C1 | 1 | Création du fxml pour le SignUp view | Dave | Ismael | 1 | 2 |  | Done
C1-24 | 1 | C1 | 1 | Création des contrôleurs pour chaque vue pour gérer les interactions avec l’utilisateur | Dave | Ismael | 1 | 0.5 |  | Done
C1-25 | 1 | C1 | 1 | Implémentation de la logique d'authentification dans les contrôleurs en utilisant les API JavaFX et JFoenix pour les éléments graphiques | Dave | Ismael | 1.5 | 1 |  | Done
C1-26 | 1 | C1 | 1 | Liaison des vues d’authentification avec le modèle | Dave | Ismael | 1.5 | 2.5 |  | Done
C1-27 | 1 | C1 | 1 | Refactoring | Dave | Ismael | 0.5 | 0.5 |  | Done
C1-28 | 1 | C1 | 1 | Gestion des erreurs liées aux dépendances et aux conflits | Dave | Ismael | 0.25 | 1 |  | Done
C3-1 | 1 | C3 | 1 | Création vue Deck edit | Elliot | Francesco | 1.5 | 2.5 |  | Done
C3-2 | 1 | C3 | 1 | Documentation Javadoc | Francesco | Elliot | 0.5 | 0.5 |  | Done
C3-3 | 1 | C3 | 1 | Tests unitaires deck et card | Francesco | Elliot | 0.5 | 0.5 |  | Done
C3-4 | 1 | C3 | 1 | Refactor global | Francesco | Elliot | 1 | 0.5 |  | Done
C3-5 | 1 | C3 | 1 | Création classe vue | Francesco | Elliot | 2 | 3 |  | Done
C3-6 | 1 | C3 | 1 | Création controller de la vue deck edit | Francesco | Elliot | 2.5 | 3 |  | Done
C3-7 | 1 | C3 | 1 | Liaison entre les deux controllers de DeckView | Francesco | Elliot | 1.5 | 1 |  | Done
C3-8 | 1 | C3 | 1 | Création des classes modèles | Emile | Théo | 2 | 2.5 |  | Done
C3-9 | 1 | C3 | 1 | Refactor code pour lier la vue et le controlleur | Théo | Emile | 1.5 | 2 |  | Done
C3-10 | 1 | C3 | 1 | Liaison avec la deck view | Théo | Emile | 1 | 1 |  | Done
C3-11 | 1 | C3 | 1 | Création de tests pour les classes modèles | Emile | Théo | 1 | 0.5 |  | Done
C2-1 | 2 | C2 | 1 | DB: Create Deck & Card model in database (CRUD) | Dave | Anton | 2 | 10 |  | Done
C2-2 | 2 | C2 | 1 | EditDeck (FXML): Create global title and edit buttons | Elliot | Antoine | 1 | 1.5 |  | Done
C2-3 | 2 | C2 | 1 | EditDeck (FXML): Create deck list table | Elliot | Antoine | 2 | 2.5 |  | Done
C2-4 | 2 | C2 | 1 | EditDeck (DeckEditController): Load fake deck cards dynamically in list | Antoine | Elliot | 1 | 0.5 |  | Done | To be linked with database
C2-5 | 2 | C2 | 1 | EditDeck(FXML): Edit button popup to edit question and answer | Antoine | Elliot | 2 | 2 |  | Done
C2-6 | 2 | C2 | 1 | EditDeck(DeckEditController): Edit button logic to edit question and answer in popup | Antoine | Elliot | 2 | 1 |  | Done | To be linked with database
C2-7 | 2 | C2 | 1 | EditDeck(FXML): Delete button to delete question | Antoine | Elliot | 1 | 0.5 |  | Done
C2-8 | 2 | C2 | 1 | EditDeck(DeckEditController): Delete button logic to delete question | Elliot | Antoine | 2 | 0.5 |  | Done
C2-9 | 2 | C2 | 1 | EditDeck(DeckEditController) : Edit deck properties logic (title, category) | Elliot | Antoine | 3 | 0.5 |  | Done
C2-10 | 2 | C2 | 1 | Deck List: Deck creation & deletion from the view | Théo | Luca | 3 | 2.5 |  | Done
C2-11 | 2 | C2 | 1 | Deck List: Load decks from the database in the view | Théo | Luca | 3 | 1 |  | Done
C2-12 | 2 | C2 | 1 | Deck List: Filter deck by category/theme | Antoine | Ismael | 4 | 3.5 |  | Done
C2-13 | 2 | C2 | 1 | DeckList (FXML): Delete button warning popup to delete deck & card | Théo | Dave | 1 | 0.5 |  | Done
C2-14 | 2 | C2 | 1 | DeckList (ProfileController): Pass deck ID from profile view to deckEdit view when pushing edit btn | Elliot | Antoine | 2 | 1 |  | Done | See node.getScene().getWindow() and stage.setUserData()
C2-15 | 2 | C2 | 1 | EditDeck(FXML): Add card popup | Antoine | Elliot | 1 | 0.5 |  | Done
C2-16 | 2 | C2 | 1 | EditDeck(FXML): edit title and category popups | Antoine | Elliot | 1 | 0.5 |  | Done
C2-18 | 2 | C2 | 1 | EditDeck(FXML): make vboxes question/answer for cards | Luca | Antoine | 2 | 1 |  | Done
C2-19 | 2 | C2 | 2 | EditDeck(docs): make docstrings and comments for all classes | Francesco |  | 2 | 2.5 |  | Done
C2-20 | 2 | C2 | 1 | EditDeck(FXML): Add scrolling in edit deck view | Antoine | Luca | 2 | 0.5 |  | Done
C2-21 | 2 | C2 | 1 | DeckList(FXML): Add scrolling in DeckList/Profile/settings view | Ismael | Dave | 1.5 | 1 |  | Done
C2-22 | 2 | C2 | 1 | DeckList(FXML): text wrapping for DeckList/Profile view | Dave | Ismael | 1 | 1 |  | Done
C2-23 | 2 | C2 | 1 | EditDeck(FXML): add category in view | Dave | Ismael | 2 | 2 |  | Done
C2-25 | 2 | C2 | 2 | EditDeck(FXML): warning popup before deleting card | Elliot | Antoine | 0.5 | 0 |  | Done
C2-26 | 2 | C2 | 1 | Fix(Database): Tables are created only when calling getInstance() | Luca | Ismael | 1 | 0.5 |  | Done
C2-27 | 2 | C2 | 1 | DB: Create interface between controller & database for managing decks & cards | Luca | Francesco | 2 | 3 |  | Done
C2-28 | 2 | C2 | 1 | Refactor(Database): Remove the perfomanceType entity (replace with simple integer) | Dave |  | 0.5 | 0.5 |  | Done
C2-29 | 2 | C2 | 1 | Fix(Database): Fixed issue in test caused by database, refactor database | Luca |  | 3 | 2.5 |  | Done
C4-1 | 2 | C4 | 1 | Study: Refactor the editDeck view into the static Study view (FlashCard view) | Luca | Emile | 8 | 3 |  | Done
C4-2 | 2 | C4 | 1 | Study: Load cards from database into Study view | Emile | Théo | 4 | 4.5 |  | Done
C4-4 | 2 | C4 | 1 | Study: Add text wrapping in Study view for answer & question | Francesco | Ismael | 1 | 0.5 |  | Done
C6-1 | 2 | C6 | 2 | Study Mode: Implement the "Review" study mode | Ben David | Francesco | 8 | 6 |  | Done
C6-2 | 2 | C6 | 2 | Study Mode: Implement the "Free" study mode | Ben David | Francesco | 8 | 4 |  | Done
C6-3 | 2 | C6 | 1 | Study Mode: Create a controller for "Review" Mode | Francesco | Luca | 4 | 4 |  | Done
C6-4 | 2 | C6 | 1 | Study Mode: Implements the tests | Francesco | Ben David | 2 | 1.5 |  | Done
C6-5 | 2 | C6 | 1 | Study Mode: Refactor Sutdy views and handle exceptions | Dave | Théo | 4 | 4 |  | Done
C6-6 | 2 | C6 | 2 | Study Mode: create a view for "Free" study mode | Anton | Théo | 1 | 1.5 |  | Done
D1-1 | 2 | D1 | 3 | CI/CD: Create a CI/CD action to test, check format & build | Anton | Ben David | 5 | 3.5 |  | Done
D2-1 | 2 | D2 | 1 | Refactor: Split the SignIn & SignUp controller | Francesco | Dave | 1 | 1 |  | Done
D2-2 | 2 | D2 | 1 | Refactor: Split the Profile & Settings Controller | Luca | Ismael | 1 | 2 |  | Done
D2-3 | 2 | D2 | 3 | Refactor: Fix layout for the SignIn & SignUp view | Francesco | Dave | 3 | 1 |  | Done
D3-1 | 2 | D3 | 3 | Tracking: task excel on google sheets | Antoine | Luca | 1 | 1 |  | Done
D3-2 | 2 | D3 | 3 | Tracking: Burndown Chart | Luca | Antoine | 1 | 1 |  | Done
D4-1 | 2 | D4 | 3 | Docs: refaire le README.md | Francesco |  | 0.5 | 0.5 |  | Done
D5-1 | 2 | D5 | 1 | Refactor: navigation manager design | Luca | Antoine | 1 | 1 |  | Done
D5-2 | 2 | D5 | 1 | Refactor: navigation manager implementation | Luca | Antoine | 1 | 1 |  | Done
D5-3 | 2 | D5 | 1 | Feat: Add params in navigation | Luca | Antoine | 1.5 | 1.5 |  | Done
D6-1 | 2 | D6 | 1 | Refactor: handling all runtime errors in code; replace signature errors in try/catch blocks | Francesco | Ismael | 2 | 3 |  | Done | We don't know how to handle database errors, need help
C10-1 | 3 | C10 | 1 | Server: Setup Django App with Docker Compose (Initial Setup) + Architecture | Elliot | Anton | 4 | 3 |  | Done
C10-10 | 3 | C10 | 1 | Server: Add API for Sign Up (create an account) + edit password | Anton | Ismael | 2 | 1 |  | Done
C10-11 | 3 | C10 | 2 | Server: Bug fixes and tags server side | Anton | Francesco | 2 | 2 |  | Done
C10-13 | 3 | C10 | 1 | Refactor services | Dave |  | 2 | 3 |  | Done
C10-13 | 3 | C10 | 1 | Server tags deletion | Anton | Ben David | 1 | 3 |  | Done
C10-2 | 3 | C10 | 1 | Server: ORM Models in Django + Admin Interface | Dave | Anton | 3 | 3 |  | Done
C10-3 | 3 | C10 | 1 | Server: Serializers and Deserializers (JSON) | Antoine | Luca | 3 | 1 |  | Done
C10-4 | 3 | C10 | 1 | Server: Deployment (on Cloud) + DNS | Ben David | Luca | 3 | 4.5 |  | Done
C10-5 | 3 | C10 | 2 | Server: Generate Swagger docs | Ismael | Théo | 2 | 2 |  | Done
C10-6 | 3 | C10 | 2 | Client: Refactor services (Call HTTP API) | Francesco | Dave | 3 | 6 |  | Done
C10-7 | 3 | C10 | 2 | Client: Refactor services (Call HTTP API) with swapped pilot-copilot | Dave | Francesco | 4 | 5 |  | Done
C10-8 | 3 | C10 | 1 | Finish setting up docker and django | Anton | Francesco | 2 | 2.5 |  | Done
C10-9 | 3 | C10 | 1 | Finish api (tests + security) | Anton | Dave | 3 | 0 |  | Done
C15-1 | 3 | C15 | 1 | FXML: Add dropdown buttons on the UI to Export/Import JSON on the ProfileView + File Browser + PDF | Elliot | Emile | 3 | 2 |  | Done
C15-2 | 3 | C15 | 1 | Export/import: Serialize/Deserialize deck (JSON) and export to file (or create deck) | Elliot | Emile | 6 | 5.5 |  | Done
C15-3 | 3 | C15 | 1 | Export/Import: Rewrite tests | Emile |  | 1 | 1 |  | Done
C16-1 | 3 | C16 | 1 | FXML: Add buttons on the UI to download PDF (Add option in Export ?) | Antoine | Dave | 3 | 0.5 |  | Done
C16-2 | 3 | C16 | 1 | PDF: Add logic to download PDF | Antoine | Dave | 5 | 2 |  | Done
C16-3 | 3 | C16 | 2 | PDF: Format PDF | Dave | Antoine | 2 | 1 |  | Done
C16-4 | 3 | C16 | 3 | PDF: format A6 for cards | Antoine | Ismael | 2 | 3 |  | Done
C16-5 | 3 | C16 | 3 | PDF: Add popup when a deck is downloaded | Dave | Antoine | 0.5 | 0.5 |  | Done
C17-11 | 3 | C17 | 1 | FXML + Client + Refactor: Refactor HTML, LaTeX, plain text into learning mode | Francesco | Ben David | 1.5 | 1 |  | Done
C17-2 | 3 | C17 | 1 | Client: Parse LaTeX | Ismael | Francesco | 5 | 1 |  | Done
C17-3 | 3 | C17 | 1 | Client: Parse HTML | Ben David | Dave | 5 | 2 |  | Done
C17-4 | 3 | C17 | 1 | FXML: Create a radio button when inputting card to let the user decide what kind of input he wants | Dave | Ismael | 2 | 1.5 |  | Done
C17-5 | 3 | C17 | 1 | FXML:: Create a webView when studying HTML | Théo | Ben David | 3 | 2.5 |  | Done
C17-6 | 3 | C17 | 1 | Django DB: Add question type and answer type to database | Ismael | Anton | 3 | 3 |  | Done
C17-7 | 3 | C17 | 1 | FXML + Client: Add latexView in editDeck | Francesco | Ben David | 3 | 3 |  | Done
C17-8 | 3 | C17 | 1 | FXML + Client: Add latexView in learningMode | Ben David | Francesco | 2 | 1.5 |  | Done
C17-9 | 3 | C17 | 1 | FXML + Client: Add HTMLView in editDeck | Ben David | Ismael | 3 | 5 |  | Done
D7-1 | 3 | D7 | 1 | Refactor: fix refresh list when adding new decks with unknown tag | Antoine | Ismael | 2 | 1.5 |  | Done
D7-10 | 3 | D7 | 2 | Refactor: Manage the navigation in a different way (controller should choose to change view!) | Luca | Ismael | 3 | 2.5 |  | Done
D7-11 | 3 | D7 | 2 | FXML: Popups should be styled the same as the rest of the application | Théo | Ismael | 4 | 3 |  | Done
D7-11-1 | 3 | D7 | 3 | FXML: Empty EditCardView : Question/Answer is empty ¦ CreateDeck : Deckname/Tag is empty--> Add Popup | Ismael |  | 1 | 0 |  | Done
D7-12 | 3 | D7 | 2 | MVC: Refactor the view controllers and controllers to respect the MVC patterns | Luca |  | 3 | 4 |  | Done
D7-13 | 3 | D7 | 3 | ci: refactor CI/CD + build Django docker image | Luca |  | 2 | 2 |  | Done
D7-14 | 3 | D7 | 3 | CreateCard: add length limit to size of question and answer (e.g. max 250 chars per question or per answer) | Théo | Ismael | 2 | 2.5 |  | Done
D7-15 | 3 | D7 | 1 | Refactor + FXML + Client: Fix Review Mode | Francesco |  | 2 | 1.5 |  | Done
D7-7 | 3 | D7 | 1 | Service: Create a UserService with DTOs + Refactor | Luca | Théo | 3 | 5 |  | Done
C10-15 | 3 | C10 | 1 | fix tags in UI + refactor | Anton | Ben David | 2 | 4 |  | Done
C10-16 | 3 | C10 | 1 | API Client bug fixes | Dave | Anton | 4 | 3 |  | Done
D7-17 | 3 | D7 | 2 | Refactor error handling | Anton |  | 2 | 2 |  | Done
D7-18 | 3 | D7 | 1 | Bug: fix the json deck exporter file chooser not working properly | Antoine | Emile | 1 | 1 |  | Done
C17-12 | 3 | C17 | 1 | Refactor + client + server: Make card use card type and not be statically bound | Francesco | Anton | 1.5 | 2 |  | Done
D7-19 | 3 | D7 | 2 | Refactor: Profile view add deck mth | Antoine |  | 1 | 1 |  | Done
C11-001 | 4 | C11 | 1 | Database: Review Database model for the store + API | Luca | Elliot | 3 | 3.5 |  | Done
C11-003 | 4 | C11 | 1 | FXML: Add View for store + ViewController | Elliot | Antoine | 6 | 5 |  | Done
C11-004 | 4 | C11 | 1 | FXML: add carousel for most popular decks | Elliot | Antoine | 5 | 5 |  | Done
C11-005 | 4 | C11 | 1 | FXML: show all decks on the store | Antoine | Elliot | 4 | 1.5 |  | Done
C11-006 | 4 | C11 | 1 | StoreDeckService: api call for popular and all decks | Antoine | Luca | 3 | 1.5 |  | Done
C11-007 | 4 | C11 | 1 | StoreDeckService: download storedeck api call | Antoine | Luca | 2 | 0.5 |  | Done
C11-008 | 4 | C11 | 1 | StoreDeckService : share deck api call | Luca | Antoine | 2 | 0.5 |  | Done
C11-009 | 4 | C11 | 1 | StoreDeckService: search for deck in catalog | Antoine | Elliot | 2 | 1 |  | Done
C11-010 | 4 | C11 | 2 | ProfileView: popup to confirm sharing the deck | Antoine | Elliot | 0 | 0 |  | Done
C11-011 | 4 | C11 | 2 | StoreDeckView: popup to confirm that the deck has been downloaded | Antoine | Elliot | 0 | 0 |  | Done
C14-001 | 4 | C14 | 2 | FXML: Add button with Speaker Icon in learning modes | Dave | Francesco | 1 | 1 |  | Done
C14-002 | 4 | C14 | 2 | FXML: Add logic to dictate answer OR question in Controller | Francesco | Dave | 1.5 | 2 |  | Done | Need other tasks to be completed before starting this one!
C8-002 | 4 | C8 | 1 | FXML: Question Type and Answer Type should be in the card dialog | Luca | Dave | 5 | 3.5 |  | Done
C8-003 | 4 | C8 | 1 | FXML: Handle different card type in all learning mode | Dave | Emile | 8 | 11 |  | Done
C8-004 | 4 | C8 | 1 | Model: Handle different card type in Cards | Francesco | Dave | 2 | 1.5 |  | Done
C9-001 | 4 | C9 | 1 | Database: Model for statistics + Django API | Anton | Antoine | 6 | 9 |  | Done
C9-002 | 4 | C9 | 1 | Service: Create a Service for the Statistics API | Ben David | Théo | 5 | 7 |  | Done
C9-004 | 4 | C9 | 1 | FXML: Add menu for GLOBAL stats (between Home and Settings) | Théo | Ismael | 6 | 21 |  | Done
D8-001 | 4 | D8 | 1 | Fix: Fix issue in import/export | Emile | Elliot | 0.5 | 0.5 |  | Done
D8-003 | 4 | D8 | 1 | Tests: tests for userService | Luca | Dave | 1 | 1.5 |  | Done
D8-004 | 4 | D8 | 1 | Tests: Configure Mockito + tests for tagService | Dave | Luca | 1 | 1.5 |  | Done
D8-005 | 4 | D8 | 2 | Tests: Write/Update Tests for existing services | Ismael | Antoine | 4 | 0 |  | Done
D8-006 | 4 | D8 | 3 | FXML: Add help button in modes and edit card dialog to show how to format questions | Théo | Emile | 4 | 4 |  | Done
D8-007 | 4 | D8 | 2 | DP: Use the Visitor Design Pattern to handle different modes | Francesco |  | 2 | 1 |  | Done
D8-008 | 4 | D8 | 1 | Cache: Cache decks and make it not make it a request everytime | Emile | Anton | 3 | 2.5 |  | Done
D8-009 | 4 | D8 | 1 | Refactor: Use SonarLint to refactor code | Francesco |  | 2 | 2.5 |  | Done
D8-010 | 4 | D8 | 2 | Thread: Make PDF use a thread to not block the execution of the app | Ben David | Francesco | 1 | 1 |  | Done
D8-011 | 4 | D8 | 2 | PDF: Make PDF download choose location to save | Francesco | Ben David | 0.5 | 1 |  | Done
D8-013 | 4 | D8 | 2 | Refactor: Remove calculation logic outside of model | Francesco | Luca | 2.5 | 1.5 |  | Done
D8-014 | 4 | D8 | 1 | Refactor: Create custom component for Deck in ProfileDeckViewController | Francesco | Ben David | 2 | 0.5 |  | Done
D8-015 | 4 | D8 | 1 | Refactor: Create custom component for Card in EditDeckViewController | Ben David | Francesco | 1.5 | 2.5 |  | Done
D8-016 | 4 | D8 | 1 | Refactor: Create custom component for Deck in StoreDeckViewController - Spotlight | Antoine |  | 2 | 1 |  | Done
D8-017 | 4 | D8 | 1 | Refactor: Create custom component for Deck in StoreDeckViewController - Populars | Luca |  | 1 | 2.5 |  | Done
D8-019 | 4 | D8 | 1 | Refactor: Add method for TextInputDialog | Luca |  | 1 | 0.5 |  | Done
D8-020 | 4 | D8 | 1 | Refactor: Fix issues with Docker + add persistent volume for Postgres Database | Luca | Anton | 1 | 0.5 |  | Done
D8-021 | 4 | D8 | 1 | Refactor: Add method in AbstractViewController to open FileBrowser | Luca |  | 0.5 | 0.5 |  | Done
D8-022 | 4 | D8 | 2 | Feature: progress indicator for API calls | Anton |  | 5 | 5 |  | Done
D8-024 | 4 | D8 | 1 | Refactor: Create different card components for edit and learning code + refactor code out of models | Francesco | Luca | 4 | 0 |  | Done
D8-025 | 4 | D8 | 1 | Refactor: D8-024 with different pilots | Luca | Francesco | 3 | 3.5 |  | Done
D8-026 | 4 | D8 | 1 | Refactor: Remove card and replace it with abstract card and replace instantiation in services with parsers | Francesco | Luca | 5 | 7.5 |  | Done
D8-027 | 4 | D8 | 1 | Code: General code refactor | Francesco |  | 2 | 2 |  | Done
D8-028 | 4 | D8 | 2 | FXML + Client: Make user not go to review mode if deck is empty | Francesco | Théo | 0.5 | 0.5 |  | Done
D8-029 | 4 | D8 | 2 | Learning Mode: check all learning views and controllers (add docstrings, remove fixme, remove controls in view) | Dave |  | 2 | 2.5 |  | Done
D8-030 | 4 | D8 | 2 | Tests: tests model for all modes | Dave | Ismael | 1 | 2 |  | Done
D8-031 | 4 | D8 | 2 | Text to speech: remove static methods | Ismael |  | 0.5 | 1 |  | Done
D8-032 | 4 | D8 | 1 | Javadoc |  |  | 4 | 4 |  | Done
D8-033 | 4 | D8 | 1 | Demo | Dave |  | 1 | 1.5 |  | Done
D8-034 | 4 | D8 | 1 | Fix old Jar files | Ben David | Dave | 0.5 | 0.5 |  | Done
D8-035 | 4 | D8 | 2 | Refactor: EditCardDialog | Emile | Théo | 4 | 4 |  | Done
D8-037 | 4 | D8 | 1 | Test parsers | Elliot |  | 2 | 2 |  | Done
D8-040 | 4 | D8 | 1 | handle cloze based text card on edit Deck view | Dave | Ben David | 2 | 2 |  | Done
Note on E98: Use the HTTPClient Java API from java.net.http
Note on E127: Use the Factory DP, this makes it easier to test the different services

## Calendar
2 | Backlog |  | Progress |  | Estimated Total |  |  |  | Iteration 2 (Week 1) | [13 empty] | Iteration 2 (Week 2) | [13 empty] | Iteration 2 (Week 3)
| Estimate/Iteration |  | Estimate/Iteration |  | Estimate/Iteration |  | Total/Iteration |  | 2023-03-14 |  | 2023-03-15 |  | 2023-03-16 |  | 2023-03-17 |  | 2023-03-18 |  | 2023-03-19 |  | 2023-03-27 |  | 2023-03-28 |  | 2023-03-29 |  | 2023-03-30 |  | 2023-03-31 |  | 2023-04-01 |  | 2023-04-02 |  | 2023-04-17 |  | Iteration 2 has no Week 3
Members | P | COP | P | COP | P | COP | P | COP | P | COP | P | COP | P | COP | P | COP | P | COP | P | COP | P | COP | P | COP | P | COP | P | COP | P | COP | P | COP | P | COP | P | COP
Dave | 0 | 0 | 0 | 0 | 14 | 10 | 14 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 4 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 5 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Anton | 0 | 0 | 0 | 0 | 6.5 | 7 | 6.5 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ismael | 0 | 0 | 0 | 0 | 2 | 11.5 | 2 | 11.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 3.5 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Luca | 0 | 0 | 0 | 0 | 15.5 | 8 | 15.5 | 8 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 2 | 0 | 3 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0.5 | 0 | 0 | 0.5 | 0 | 7 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Antoine | 0 | 0 | 0 | 0 | 11.5 | 11 | 11.5 | 11 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 1 | 0 | 0 | 3.5 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 3.5 | 0.5 | 1 | 0 | 0 | 0 | 0 | 3.5 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ben David | 0 | 0 | 0 | 0 | 10 | 7.5 | 10 | 7.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 4 | 0 | 0 | 2.5 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Francesco | 0 | 0 | 0 | 0 | 16.5 | 13 | 16.5 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 6 | 0 | 4 | 2.5 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Elliot | 0 | 0 | 0 | 0 | 5.5 | 6.5 | 5.5 | 6.5 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 3.5 | 0 | 2 | 0 | 0 | 0 | 0 | 3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Théo | 0 | 0 | 0 | 0 | 5 | 8.5 | 5 | 8.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 8.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Emile | 0 | 0 | 0 | 0 | 4.5 | 3 | 4.5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Totals | 0 | 0 | 0 | 0 | 91 | 86 | 91 | 86 | 0 | 0 | 0 | 0 | 4 | 4 | 5 | 5 | 0 | 0 | 15.5 | 15.5 | 14.5 | 14.5 | 2.5 | 2.5 | 1.5 | 1.5 | 3.5 | 3.5 | 1.5 | 1.5 | 0 | 0 | 8.5 | 8.5 | 34.5 | 29.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | Backlog |  | Progress |  | Estimated Total |  |  |  | Iteration 3 (Week 1) | [13 empty] | Iteration 3 (Week 2) | [13 empty] | Iteration 3 (Week 3)
| Estimate/Iteration |  | Estimate/Iteration |  | Estimate/Iteration |  | Total/Iteration |  | 2023-04-18 |  | 2023-04-19 |  | 2023-04-20 |  | 2023-04-21 |  | 2023-04-22 |  | 2023-04-23 |  | 2023-04-24 |  | 2023-04-25 |  | 2023-04-26 |  | 2023-04-27 |  | 2023-04-28 |  | 2023-04-29 |  | 2023-04-30 |  | 2023-05-01 |  | Iteration 3 has no Week 3
Members | P | COP | P | COP | P | COP | P | COP | P | COP | P | COP | P | COP | P | COP | P | COP | P | COP | P | COP | P | COP | P | COP | P | COP | P | COP | P | COP | P | COP | P | COP
Dave | 0 | 0 | 0 | 0 | 16 | 12.5 | 16 | 12.5 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 2.5 | 1.5 | 0 | 1.5 | 4 | 0 | 0 | 0 | 0 | 5 | 6 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Anton | 0 | 0 | 0 | 0 | 14.5 | 14 | 14.5 | 14 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 2.5 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 3 | 3 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ismael | 0 | 0 | 0 | 0 | 9.5 | 15.5 | 9.5 | 15.5 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0.5 | 0.5 | 1.5 | 2 | 3 | 0 | 5 | 6 | 0 | 0 | 1 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Luca | 0 | 0 | 0 | 0 | 13.5 | 5.5 | 13.5 | 5.5 | 3 | 0 | 1 | 0 | 2 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0.5 | 0 | 0 | 0 | 2 | 0 | 1 | 3 | 0 | 0 | 0 | 1.5 | 1 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Antoine | 0 | 0 | 0 | 0 | 7 | 4.5 | 7 | 4.5 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 2.5 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ben David | 0 | 0 | 0 | 0 | 11.5 | 8.5 | 11.5 | 8.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 8 | 0 | 0 | 5.5 | 1.5 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Francesco | 0 | 0 | 0 | 0 | 12.5 | 10.5 | 12.5 | 10.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 5 | 0 | 2 | 1.5 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Elliot | 0 | 0 | 0 | 0 | 10.5 | 0 | 10.5 | 0 | 0 | 0 | 3 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 1 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Théo | 0 | 0 | 0 | 0 | 8 | 7 | 8 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 0 | 1 | 2.5 | 0 | 0 | 0 | 0 | 1 | 2.5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Emile | 0 | 0 | 0 | 0 | 1 | 8.5 | 1 | 8.5 | 0 | 0 | 0 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 1 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Totals | 0 | 0 | 0 | 0 | 104 | 86.5 | 104 | 86.5 | 4.5 | 0 | 4 | 3 | 3.5 | 3.5 | 3 | 3 | 1 | 1 | 2.5 | 2.5 | 5.5 | 5.5 | 7.5 | 7 | 7 | 5 | 9 | 9 | 22.5 | 22.5 | 6.5 | 6.5 | 12.5 | 8 | 15 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | Backlog |  | Progress |  | Estimated Total |  |  |  | Iteration 4 (Week 1) | [13 empty] | Iteration 4 (Week 2) | [13 empty] | Iteration 4 (Week 3)
| Estimate/Iteration |  | Estimate/Iteration |  | Estimate/Iteration |  | Total/Iteration |  | 2023-05-02 |  | 2023-05-03 |  | 2023-05-04 |  | 2023-05-05 |  | 2023-05-06 |  | 2023-05-07 |  | 2023-05-08 |  | 2023-05-09 |  | 2023-05-10 |  | 2023-05-11 |  | 2023-05-12 |  | 2023-05-13 |  | 2023-05-14 |  | 2023-05-15 |  | 2023-05-16 |  | 2023-05-17 |  | 2023-05-18 |  | 2023-05-19 |  | 2023-05-20 |  | 2023-05-21 |  | 2023-05-22
Members | P | COP | P | COP | P | COP | P | COP | P | COP | P | COP | P | COP | P | COP | P | COP | P | COP | P | COP | P | COP | P | COP | P | COP | P | COP | P | COP | P | COP | P | COP | P | COP | P | COP | P | COP | P | COP | P | COP | P | COP | P | COP
Dave | 0 | 0 | 0 | 0 | 21.5 | 9 | 21.5 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 3.5 | 7 | 4.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.5 | 0 | 3.5 | 0.5
Anton | 0 | 0 | 0 | 0 | 12 | 3.5 | 12 | 3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 6 | 0 | 0 | 3 | 0 | 0.5 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ismael | 0 | 0 | 0 | 0 | 15 | 9 | 15 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 0
Luca | 0 | 0 | 0 | 0 | 19.5 | 12.5 | 19.5 | 12.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 2 | 0 | 0 | 1.5 | 0 | 4.5 | 0 | 0.5 | 2 | 2 | 0.5 | 0.5 | 0 | 0 | 0 | 6.5 | 0 | 3 | 1.5 | 0 | 0 | 0 | 3 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0
Antoine | 0 | 0 | 0 | 0 | 11 | 12.5 | 11 | 12.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1.5 | 11 | 2 | 0.5 | 3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0
Ben David | 0 | 0 | 0 | 0 | 12.5 | 14 | 12.5 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5 | 0 | 3.5 | 0 | 2 | 2.5 | 1 | 0 | 0 | 8.5 | 1 | 0 | 1 | 0.5 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0.5 | 2
Francesco | 0 | 0 | 0 | 0 | 18.5 | 12 | 18.5 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.5 | 0 | 0 | 2 | 3 | 0 | 0 | 1 | 0.5 | 1 | 0 | 5 | 0 | 3 | 0 | 0 | 3 | 0 | 1.5 | 0 | 3 | 0 | 0 | 0 | 0 | 0
Elliot | 0 | 0 | 0 | 0 | 12.5 | 6 | 12.5 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 2 | 0 | 1.5 | 0 | 0 | 1.5 | 5 | 2.5 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0
Théo | 0 | 0 | 0 | 0 | 9.5 | 19 | 9.5 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 6 | 1.5 | 0 | 3.5 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 4
Emile | 0 | 0 | 0 | 0 | 7 | 12 | 7 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 3.5 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 2.5
Totals | 0 | 0 | 0 | 0 | 139 | 109.5 | 139 | 109.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 5 | 5 | 11 | 9.5 | 6 | 6 | 30 | 28.5 | 11 | 9.5 | 14.5 | 10.5 | 9.5 | 9 | 6.5 | 1.5 | 6.5 | 6.5 | 6.5 | 4.5 | 0 | 0 | 3 | 3 | 1.5 | 1.5 | 3 | 0.5 | 8.5 | 2 | 13.5 | 9

## Burndown Overview
Story | Estimate | 1 | 2 | 3 | 4 | Totals | 390.5 | 338 | 249.5 | 142.5 | 5
C1 | 23 | -12.5 | -12.5 | -12.5 | -12.5
C2 | 48.5 | 48.5 | 5.5 | 5.5 | 5.5
C3 | 15 | -2 | -2 | -2 | -2
C4 | 13 | 13 | 5 | 5 | 5
C5 | 0 | 0 | 0 | 0 | 0
C6 | 27 | 27 | 6 | 6 | 6
C7 | 0 | 0 | 0 | 0 | 0
C8 | 15 | 15 | 15 | 15 | -1
C9 | 17 | 17 | 17 | 17 | -20
C10 | 40 | 40 | 40 | -3 | -3
C11 | 27 | 27 | 27 | 27 | 8.5
C12 | 0 | 0 | 0 | 0 | 0
C13 | 0 | 0 | 0 | 0 | 0
C14 | 2.5 | 2.5 | 2.5 | 2.5 | -0.5
C15 | 10 | 10 | 10 | 1.5 | 1.5
C16 | 12.5 | 12.5 | 12.5 | 5.5 | 5.5
C17 | 29 | 29 | 29 | 6.5 | 6.5
C18 | 0 | 0 | 0 | 0 | 0
C19 | 0 | 0 | 0 | 0 | 0
C20 | 0 | 0 | 0 | 0 | 0
C21 | 0 | 0 | 0 | 0 | 0
C22 | 0 | 0 | 0 | 0 | 0
D1 | 5 | 5 | 1.5 | 1.5 | 1.5
D2 | 5 | 5 | 1 | 1 | 1
D3 | 2 | 2 | 0 | 0 | 0
D4 | 0.5 | 0.5 | 0 | 0 | 0
D5 | 3.5 | 3.5 | 0 | 0 | 0
D6 | 2 | 2 | -1 | -1 | -1
D7 | 26 | 26 | 26 | 0 | 0
D8 | 67 | 67 | 67 | 67 | 4

## Iteration-1 (Burndown)
|  | SUM of | SUM of | Iteration | 1 | Total |  | C1 |  | C3
C1 | Ajout des dépendances Maven pour JavaFX et JFoenix dans le pom.xml | 0.25 | 0.5 | Jour | J | Ideal | Reel | Ideal | Reel | Ideal | Reel
| Création d’un component pour le layout | 0.5 | 1 | 2023-02-28 | 0 | 38 | 52.5 | 23 | 35.5 | 15 | 17
| Création de la vue settings | 1 | 0.5 | 2023-03-01 | 1 | 35.0769 | 48 | 21.2308 | 31 | 13.8462 | 17
| Création des contrôleurs pour chaque vue pour gérer les interactions avec l’utilisateur | 1 | 0.5 | 2023-03-02 | 2 | 32.1538 | 35 | 19.4615 | 21 | 12.6923 | 14
| Création du fxml pour le SignIn view | 1 | 2 | 2023-03-03 | 3 | 29.2308 | 27 | 17.6923 | 13 | 11.5385 | 14
| Création du fxml pour le SignUp view | 1 | 2 | 2023-03-04 | 4 | 26.3077 | 23 | 15.9231 | 9 | 10.3846 | 14
| Création styles de base | 1 | 2 | 2023-03-05 | 5 | 23.3846 | 20 | 14.1538 | 6 | 9.2308 | 14
| Création tables User et tests | 1 | 1 | 2023-03-06 | 6 | 20.4615 | 16 | 12.3846 | 6 | 8.0769 | 10
| Création UserDatabase et tests | 1 | 1 | 2023-03-07 | 7 | 17.5385 | 16 | 10.6154 | 6 | 6.9231 | 10
| Création vue profil | 1 | 1 | 2023-03-08 | 8 | 14.6154 | 14 | 8.8462 | 6 | 5.7692 | 8
| Documentation Javadoc | 0.5 | 1 | 2023-03-09 | 9 | 11.6923 | 12 | 7.0769 | 4 | 4.6154 | 8
| Génération dynamique d’éléments UI dans profil et settings | 0.5 | 0.5 | 2023-03-10 | 10 | 8.7692 | 7 | 5.3077 | 1 | 3.4615 | 6
| Gestion des erreurs liées aux dépendances et aux conflits | 0.25 | 1 | 2023-03-11 | 11 | 5.8462 | 5 | 3.5385 | 1 | 2.3077 | 4
| Implémentation algo hash et tests | 1 | 1.5 | 2023-03-12 | 12 | 2.9231 | 1 | 1.7692 | 0 | 1.1538 | 1
| Implémentation de la logique d'authentification dans les contrôleurs en utilisant les API JavaFX et JFoenix pour les éléments graphiques | 1.5 | 1 | 2023-03-13 | 13 | 0 | 0 | 0 | 0 | 0 | 0
| Installation et configuration de JavaFX, Maven et Scene-Builder | 1 | 1
| Intégration login/signup – profil/settings – deck view | 1 | 1.5
| Liaison avec les vues login/sign up | 0.5 | 1
| Liaison des vues d’authentification avec le modèle | 1.5 | 2.5
| Liaisons avec les vues Login et Signup | 0.5 | 0.5
| Mise en place classes principales | 0.25 | 0.5
| Mise en place font custom | 0.25 | 1
| Mise en place Maven back-end | 1.5 | 4
| Mise en place Maven front-end | 0.5 | 1
| Mise en place ORM lite | 1 | 2.5
| Refactoring | 0.5 | 0.5
| Style vue profil | 1 | 2
| Style vue settings | 1 | 1
C1 Total |  | 23 | 35.5
C3 | Création classe vue | 2 | 3
| Création controller de la vue deck edit | 2.5 | 3
| Création de tests pour les classes modèles | 1 | 0.5
| Création des classes modèles | 2 | 2.5
| Création vue Deck edit | 1.5 | 2.5
| Documentation Javadoc | 0.5 | 0.5
| Liaison avec la deck view | 1 | 1
| Liaison entre les deux controllers de DeckView | 1.5 | 1
| Refactor code pour lier la vue et le controlleur | 1.5 | 2
| Refactor global | 1 | 0.5
| Tests unitaires deck et card | 0.5 | 0.5
C3 Total |  | 15 | 17
Grand Total |  | 38 | 52.5

## Iteration-2 (Burndown)
|  | SUM of | SUM of | Iteration | 2 | Total |  | C2 |  | C4 |  | C6 |  | D1 |  | D2 |  | D3 |  | D4 |  | D5 |  | D6
C2 | DB: Create Deck & Card model in database (CRUD) | 2 | 10 | Jour | J | Ideal | Reel | Ideal | Reel | Ideal | Reel | Ideal | Reel | Ideal | Reel | Ideal | Reel | Ideal | Reel | Ideal | Reel | Ideal | Reel | Ideal | Reel
| DB: Create interface between controller & database for managing decks & cards | 2 | 3 | 2023-03-14 | 0 | 106.5 | 88.5 | 48.5 | 43 | 13 | 8 | 27 | 21 | 5 | 3.5 | 5 | 4 | 2 | 2 | 0.5 | 0.5 | 3.5 | 3.5 | 2 | 3
| Deck List: Deck creation & deletion from the view | 3 | 2.5 | 2023-03-15 | 1 | 98.3077 | 88.5 | 44.7692 | 43 | 12 | 8 | 24.9231 | 21 | 4.6154 | 3.5 | 4.6154 | 4 | 1.8462 | 2 | 0.46154 | 0.5 | 3.2308 | 3.5 | 1.8462 | 3
| Deck List: Filter deck by category/theme | 4 | 3.5 | 2023-03-16 | 2 | 90.1154 | 84.5 | 41.0385 | 41 | 11 | 8 | 22.8462 | 21 | 4.2308 | 3.5 | 4.2308 | 4 | 1.6923 | 0 | 0.42308 | 0.5 | 2.9615 | 3.5 | 1.6923 | 3
| Deck List: Load decks from the database in the view | 3 | 1 | 2023-03-17 | 3 | 81.9231 | 79.5 | 37.3077 | 40.5 | 10 | 8 | 20.7692 | 21 | 3.8462 | 3.5 | 3.8462 | 0 | 1.5385 | 0 | 0.38462 | 0 | 2.6923 | 3.5 | 1.5385 | 3
| DeckList (FXML): Delete button warning popup to delete deck & card | 1 | 0.5 | 2023-03-18 | 4 | 73.7308 | 79.5 | 33.5769 | 40.5 | 9 | 8 | 18.6923 | 21 | 3.4615 | 3.5 | 3.4615 | 0 | 1.3846 | 0 | 0.34615 | 0 | 2.4231 | 3.5 | 1.3846 | 3
| DeckList (ProfileController): Pass deck ID from profile view to deckEdit view when pushing edit btn | 2 | 1 | 2023-03-19 | 5 | 65.5385 | 64 | 29.8462 | 33 | 8 | 6 | 16.6154 | 15 | 3.0769 | 3.5 | 3.0769 | 0 | 1.2308 | 0 | 0.30769 | 0 | 2.1538 | 3.5 | 1.2308 | 3
| DeckList(FXML): Add scrolling in DeckList/Profile/settings view | 1.5 | 1 | 2023-03-27 | 6 | 57.3462 | 49.5 | 26.1154 | 25.5 | 7 | 5 | 14.5385 | 11 | 2.6923 | 3.5 | 2.6923 | 0 | 1.0769 | 0 | 0.26923 | 0 | 1.8846 | 1.5 | 1.0769 | 3
| DeckList(FXML): text wrapping for DeckList/Profile view | 1 | 1 | 2023-03-28 | 7 | 49.1538 | 49.5 | 22.3846 | 25.5 | 6 | 5 | 12.4615 | 11 | 2.3077 | 3.5 | 2.3077 | 0 | 0.92308 | 0 | 0.23077 | 0 | 1.6154 | 1.5 | 0.92308 | 3
| EditDeck (DeckEditController): Load fake deck cards dynamically in list | 1 | 0.5 | 2023-03-29 | 8 | 40.9615 | 48 | 18.6538 | 25.5 | 5 | 5 | 10.3846 | 9.5 | 1.9231 | 3.5 | 1.9231 | 0 | 0.76923 | 0 | 0.19231 | 0 | 1.3462 | 1.5 | 0.76923 | 3
| EditDeck (FXML): Create deck list table | 2 | 2.5 | 2023-03-30 | 9 | 32.7692 | 44.5 | 14.9231 | 22 | 4 | 5 | 8.3077 | 9.5 | 1.5385 | 3.5 | 1.5385 | 0 | 0.61538 | 0 | 0.15385 | 0 | 1.0769 | 1.5 | 0.61538 | 3
| EditDeck (FXML): Create global title and edit buttons | 1 | 1.5 | 2023-03-31 | 10 | 24.5769 | 43 | 11.1923 | 20.5 | 3 | 5 | 6.2308 | 9.5 | 1.1538 | 3.5 | 1.1538 | 0 | 0.46154 | 0 | 0.11538 | 0 | 0.80769 | 1.5 | 0.46154 | 3
| EditDeck(DeckEditController) : Edit deck properties logic (title, category) | 3 | 0.5 | 2023-04-01 | 11 | 16.3846 | 43 | 7.4615 | 20.5 | 2 | 5 | 4.1538 | 9.5 | 0.76923 | 3.5 | 0.76923 | 0 | 0.30769 | 0 | 0.076923 | 0 | 0.53846 | 1.5 | 0.30769 | 3
| EditDeck(DeckEditController): Delete button logic to delete question | 2 | 0.5 | 2023-04-02 | 12 | 8.1923 | 34.5 | 3.7308 | 12 | 1 | 5 | 2.0769 | 9.5 | 0.38462 | 3.5 | 0.38462 | 0 | 0.15385 | 0 | 0.038462 | 0 | 0.26923 | 1.5 | 0.15385 | 3
| EditDeck(DeckEditController): Edit button logic to edit question and answer in popup | 2 | 1 | 2023-04-17 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| EditDeck(docs): make docstrings and comments for all classes | 2 | 2.5
| EditDeck(FXML): Add card popup | 1 | 0.5
| EditDeck(FXML): add category in view | 2 | 2
| EditDeck(FXML): Add scrolling in edit deck view | 2 | 0.5
| EditDeck(FXML): Delete button to delete question | 1 | 0.5
| EditDeck(FXML): Edit button popup to edit question and answer | 2 | 2
| EditDeck(FXML): edit title and category popups | 1 | 0.5
| EditDeck(FXML): make vboxes question/answer for cards | 2 | 1
| EditDeck(FXML): warning popup before deleting card | 0.5 | 0
| Fix(Database): Fixed issue in test caused by database, refactor database | 3 | 2.5
| Fix(Database): Tables are created only when calling getInstance() | 1 | 0.5
| Refactor(Database): Remove the perfomanceType entity (replace with simple integer) | 0.5 | 0.5
C2 Total |  | 48.5 | 43
C4 | Study: Add text wrapping in Study view for answer & question | 1 | 0.5
| Study: Load cards from database into Study view | 4 | 4.5
| Study: Refactor the editDeck view into the static Study view (FlashCard view) | 8 | 3
C4 Total |  | 13 | 8
C6 | Study Mode: Create a controller for "Review" Mode | 4 | 4
| Study Mode: create a view for "Free" study mode | 1 | 1.5
| Study Mode: Implement the "Free" study mode | 8 | 4
| Study Mode: Implement the "Review" study mode | 8 | 6
| Study Mode: Implements the tests | 2 | 1.5
| Study Mode: Refactor Sutdy views and handle exceptions | 4 | 4
C6 Total |  | 27 | 21
D1 | CI/CD: Create a CI/CD action to test, check format & build | 5 | 3.5
D1 Total |  | 5 | 3.5
D2 | Refactor: Fix layout for the SignIn & SignUp view | 3 | 1
| Refactor: Split the Profile & Settings Controller | 1 | 2
| Refactor: Split the SignIn & SignUp controller | 1 | 1
D2 Total |  | 5 | 4
D3 | Tracking: Burndown Chart | 1 | 1
| Tracking: task excel on google sheets | 1 | 1
D3 Total |  | 2 | 2
D4 | Docs: refaire le README.md | 0.5 | 0.5
D4 Total |  | 0.5 | 0.5
D5 | Feat: Add params in navigation | 1.5 | 1.5
| Refactor: navigation manager design | 1 | 1
| Refactor: navigation manager implementation | 1 | 1
D5 Total |  | 3.5 | 3.5
D6 | Refactor: handling all runtime errors in code; replace signature errors in try/catch blocks | 2 | 3
D6 Total |  | 2 | 3
Grand Total |  | 106.5 | 88.5

## Iteration-3 (Burndown)
|  | SUM of | SUM of | Iteration | 3 | Total |  | C10 |  | C15 |  | C16 |  | C17 |  | D7
C10 | API Client bug fixes | 4 | 3 | Jour | J | Ideal | Reel | Ideal | Reel | Ideal | Reel | Ideal | Reel | Ideal | Reel | Ideal | Reel
| Client: Refactor services (Call HTTP API) | 3 | 6 | 2023-04-18 | 0 | 117.5 | 102 | 40 | 42 | 10 | 8.5 | 12.5 | 7 | 29 | 22.5 | 26 | 22
| Client: Refactor services (Call HTTP API) with swapped pilot-copilot | 4 | 5 | 2023-04-19 | 1 | 108.4615 | 98 | 36.9231 | 39 | 9.2308 | 8.5 | 11.5385 | 7 | 26.7692 | 22.5 | 24 | 21
| Finish api (tests + security) | 3 | 0 | 2023-04-20 | 2 | 99.4231 | 94.5 | 33.8462 | 39 | 8.4615 | 7 | 10.5769 | 7 | 24.5385 | 22.5 | 22 | 19
| Finish setting up docker and django | 2 | 2.5 | 2023-04-21 | 3 | 90.3846 | 91.5 | 30.7692 | 36 | 7.6923 | 7 | 9.6154 | 7 | 22.3077 | 22.5 | 20 | 19
| fix tags in UI + refactor | 2 | 4 | 2023-04-22 | 4 | 81.3462 | 90.5 | 27.6923 | 35 | 6.9231 | 7 | 8.6538 | 7 | 20.0769 | 22.5 | 18 | 19
| Refactor services | 2 | 3 | 2023-04-23 | 5 | 72.3077 | 88 | 24.6154 | 35 | 6.1538 | 7 | 7.6923 | 4.5 | 17.8462 | 22.5 | 16 | 19
| Server tags deletion | 1 | 3 | 2023-04-24 | 6 | 63.2692 | 82.5 | 21.5385 | 32.5 | 5.3846 | 7 | 6.7308 | 3 | 15.6154 | 21.5 | 14 | 18.5
| Server: Add API for Sign Up (create an account) + edit password | 2 | 1 | 2023-04-25 | 7 | 54.2308 | 75 | 18.4615 | 30.5 | 4.6154 | 5.5 | 5.7692 | 3 | 13.3846 | 18 | 12 | 18
| Server: Bug fixes and tags server side | 2 | 2 | 2023-04-26 | 8 | 45.1923 | 68 | 15.3846 | 28.5 | 3.8462 | 5.5 | 4.8077 | 3 | 11.1538 | 18 | 10 | 13
| Server: Deployment (on Cloud) + DNS | 3 | 4.5 | 2023-04-27 | 9 | 36.1538 | 59 | 12.3077 | 25.5 | 3.0769 | 5.5 | 3.8462 | 3 | 8.9231 | 13 | 8 | 12
| Server: Generate Swagger docs | 2 | 2 | 2023-04-28 | 10 | 27.1154 | 36.5 | 9.2308 | 14.5 | 2.3077 | 5.5 | 2.8846 | 0 | 6.6923 | 4.5 | 6 | 12
| Server: ORM Models in Django + Admin Interface | 3 | 3 | 2023-04-29 | 11 | 18.0769 | 30 | 6.1538 | 10 | 1.5385 | 3.5 | 1.9231 | 0 | 4.4615 | 4.5 | 4 | 12
| Server: Serializers and Deserializers (JSON) | 3 | 1 | 2023-04-30 | 12 | 9.0385 | 17.5 | 3.0769 | 2 | 0.76923 | 1.5 | 0.96154 | 0 | 2.2308 | 4.5 | 2 | 9.5
| Server: Setup Django App with Docker Compose (Initial Setup) + Architecture | 4 | 3 | 2023-05-01 | 13 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 0 | 0
C10 Total |  | 40 | 43
C15 | Export/Import: Rewrite tests | 1 | 1
| Export/import: Serialize/Deserialize deck (JSON) and export to file (or create deck) | 6 | 5.5
| FXML: Add dropdown buttons on the UI to Export/Import JSON on the ProfileView + File Browser + PDF | 3 | 2
C15 Total |  | 10 | 8.5
C16 | FXML: Add buttons on the UI to download PDF (Add option in Export ?) | 3 | 0.5
| PDF: Add logic to download PDF | 5 | 2
| PDF: Add popup when a deck is downloaded | 0.5 | 0.5
| PDF: format A6 for cards | 2 | 3
| PDF: Format PDF | 2 | 1
C16 Total |  | 12.5 | 7
C17 | Client: Parse HTML | 5 | 2
| Client: Parse LaTeX | 5 | 1
| Django DB: Add question type and answer type to database | 3 | 3
| FXML + Client + Refactor: Refactor HTML, LaTeX, plain text into learning mode | 1.5 | 1
| FXML + Client: Add HTMLView in editDeck | 3 | 5
| FXML + Client: Add latexView in editDeck | 3 | 3
| FXML + Client: Add latexView in learningMode | 2 | 1.5
| FXML: Create a radio button when inputting card to let the user decide what kind of input he wants | 2 | 1.5
| FXML:: Create a webView when studying HTML | 3 | 2.5
| Refactor + client + server: Make card use card type and not be statically bound | 1.5 | 2
C17 Total |  | 29 | 22.5
D7 | Bug: fix the json deck exporter file chooser not working properly | 1 | 1
| ci: refactor CI/CD + build Django docker image | 2 | 2
| CreateCard: add length limit to size of question and answer (e.g. max 250 chars per question or per answer) | 2 | 2.5
| FXML: Empty EditCardView : Question/Answer is empty ¦ CreateDeck : Deckname/Tag is empty--> Add Popup | 1 | 0
| FXML: Popups should be styled the same as the rest of the application | 4 | 3
| MVC: Refactor the view controllers and controllers to respect the MVC patterns | 3 | 4
| Refactor + FXML + Client: Fix Review Mode | 2 | 1.5
| Refactor error handling | 2 | 2
| Refactor: fix refresh list when adding new decks with unknown tag | 2 | 1.5
| Refactor: Manage the navigation in a different way (controller should choose to change view!) | 3 | 2.5
| Refactor: Profile view add deck mth | 1 | 1
| Service: Create a UserService with DTOs + Refactor | 3 | 5
D7 Total |  | 26 | 26
Grand Total |  | 117.5 | 107

## Iteration-4 (Burndown)
|  | SUM of | SUM of | Iteration | 4 | Total |  | C8 |  | C9 |  | C11 |  | C14 |  | D8
C11 | Database: Review Database model for the store + API | 3 | 3.5 | Jour | J | Ideal | Reel | Ideal | Reel | Ideal | Reel | Ideal | Reel | Ideal | Reel | Ideal | Reel
| FXML: add carousel for most popular decks | 5 | 5 | 2023-05-02 | 0 | 128.5 | 138 | 15 | 16 | 17 | 37 | 27 | 18.5 | 2.5 | 3 | 67 | 63.5
| FXML: Add View for store + ViewController | 6 | 5 | 2023-05-03 | 1 | 122.075 | 138 | 14.25 | 16 | 16.15 | 37 | 25.65 | 18.5 | 2.375 | 3 | 63.65 | 63.5
| FXML: show all decks on the store | 4 | 1.5 | 2023-05-04 | 2 | 115.65 | 138 | 13.5 | 16 | 15.3 | 37 | 24.3 | 18.5 | 2.25 | 3 | 60.3 | 63.5
| ProfileView: popup to confirm sharing the deck | 0 | 0 | 2023-05-05 | 3 | 109.225 | 138 | 12.75 | 16 | 14.45 | 37 | 22.95 | 18.5 | 2.125 | 3 | 56.95 | 63.5
| StoreDeckService : share deck api call | 2 | 0.5 | 2023-05-06 | 4 | 102.8 | 135 | 12 | 16 | 13.6 | 37 | 21.6 | 16 | 2 | 3 | 53.6 | 63
| StoreDeckService: api call for popular and all decks | 3 | 1.5 | 2023-05-07 | 5 | 96.375 | 130 | 11.25 | 14 | 12.75 | 36 | 20.25 | 14 | 1.875 | 3 | 50.25 | 63
| StoreDeckService: download storedeck api call | 2 | 0.5 | 2023-05-08 | 6 | 89.95 | 119 | 10.5 | 12 | 11.9 | 28.5 | 18.9 | 12.5 | 1.75 | 3 | 46.9 | 63
| StoreDeckService: search for deck in catalog | 2 | 1 | 2023-05-09 | 7 | 83.525 | 113 | 9.75 | 12 | 11.05 | 24 | 17.55 | 11 | 1.625 | 3 | 43.55 | 63
| StoreDeckView: popup to confirm that the deck has been downloaded | 0 | 0 | 2023-05-10 | 8 | 77.1 | 83 | 9 | 3.5 | 10.2 | 16 | 16.2 | 3.5 | 1.5 | 1 | 40.2 | 59
C11 Total |  | 27 | 18.5 | 2023-05-11 | 9 | 70.675 | 72 | 8.25 | 0 | 9.35 | 16 | 14.85 | 1 | 1.375 | 0 | 36.85 | 55
C14 | FXML: Add button with Speaker Icon in learning modes | 1 | 1 | 2023-05-12 | 10 | 64.25 | 58.5 | 7.5 | 0 | 8.5 | 10 | 13.5 | 0 | 1.25 | 0 | 33.5 | 48.5
| FXML: Add logic to dictate answer OR question in Controller | 1.5 | 2 | 2023-05-13 | 11 | 57.825 | 49 | 6.75 | 0 | 7.65 | 2 | 12.15 | 0 | 1.125 | 0 | 30.15 | 47
C14 Total |  | 2.5 | 3 | 2023-05-14 | 12 | 51.4 | 42.5 | 6 | 0 | 6.8 | 2 | 10.8 | 0 | 1 | 0 | 26.8 | 40.5
C8 | FXML: Handle different card type in all learning mode | 8 | 11 | 2023-05-15 | 13 | 44.975 | 36 | 5.25 | 0 | 5.95 | 2 | 9.45 | 0 | 0.875 | 0 | 23.45 | 34
| FXML: Question Type and Answer Type should be in the card dialog | 5 | 3.5 | 2023-05-16 | 14 | 38.55 | 29.5 | 4.5 | 0 | 5.1 | 0 | 8.1 | 0 | 0.75 | 0 | 20.1 | 29.5
| Model: Handle different card type in Cards | 2 | 1.5 | 2023-05-17 | 15 | 32.125 | 29.5 | 3.75 | 0 | 4.25 | 0 | 6.75 | 0 | 0.625 | 0 | 16.75 | 29.5
C8 Total |  | 15 | 16 | 2023-05-18 | 16 | 25.7 | 26.5 | 3 | 0 | 3.4 | 0 | 5.4 | 0 | 0.5 | 0 | 13.4 | 26.5
C9 | Database: Model for statistics + Django API | 6 | 9 | 2023-05-19 | 17 | 19.275 | 25 | 2.25 | 0 | 2.55 | 0 | 4.05 | 0 | 0.375 | 0 | 10.05 | 25
| FXML: Add menu for GLOBAL stats (between Home and Settings) | 6 | 21 | 2023-05-20 | 18 | 12.85 | 22 | 1.5 | 0 | 1.7 | 0 | 2.7 | 0 | 0.25 | 0 | 6.7 | 22
| Service: Create a Service for the Statistics API | 5 | 7 | 2023-05-21 | 19 | 6.425 | 13.5 | 0.75 | 0 | 0.85 | 0 | 1.35 | 0 | 0.125 | 0 | 3.35 | 13.5
C9 Total |  | 17 | 37 | 2023-05-22 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D8 | Cache: Cache decks and make it not make it a request everytime | 3 | 2.5
| Code: General code refactor | 2 | 2
| Demo | 1 | 1.5
| DP: Use the Visitor Design Pattern to handle different modes | 2 | 1
| Feature: progress indicator for API calls | 5 | 5
| Fix old Jar files | 0.5 | 0.5
| Fix: Fix issue in import/export | 0.5 | 0.5
| FXML + Client: Make user not go to review mode if deck is empty | 0.5 | 0.5
| FXML: Add help button in modes and edit card dialog to show how to format questions | 4 | 4
| handle cloze based text card on edit Deck view | 2 | 2
| Javadoc | 4 | 4
| Learning Mode: check all learning views and controllers (add docstrings, remove fixme, remove controls in view) | 2 | 2.5
| PDF: Make PDF download choose location to save | 0.5 | 1
| Refactor: Add method for TextInputDialog | 1 | 0.5
| Refactor: Add method in AbstractViewController to open FileBrowser | 0.5 | 0.5
| Refactor: Create custom component for Card in EditDeckViewController | 1.5 | 2.5
| Refactor: Create custom component for Deck in ProfileDeckViewController | 2 | 0.5
| Refactor: Create custom component for Deck in StoreDeckViewController - Populars | 1 | 2.5
| Refactor: Create custom component for Deck in StoreDeckViewController - Spotlight | 2 | 1
| Refactor: Create different card components for edit and learning code + refactor code out of models | 4 | 0
| Refactor: D8-024 with different pilots | 3 | 3.5
| Refactor: EditCardDialog | 4 | 4
| Refactor: Fix issues with Docker + add persistent volume for Postgres Database | 1 | 0.5
| Refactor: Remove calculation logic outside of model | 2.5 | 1.5
| Refactor: Remove card and replace it with abstract card and replace instantiation in services with parsers | 5 | 7.5
| Refactor: Use SonarLint to refactor code | 2 | 2.5
| Test parsers | 2 | 2
| Tests: tests for userService | 1 | 1.5
| Tests: Configure Mockito + tests for tagService | 1 | 1.5
| Tests: tests model for all modes | 1 | 2
| Tests: Write/Update Tests for existing services | 4 | 0
| Text to speech: remove static methods | 0.5 | 1
| Thread: Make PDF use a thread to not block the execution of the app | 1 | 1
D8 Total |  | 67 | 63
Grand Total |  | 128.5 | 137.5